## Menu
Dashboard: Moldova - HIV / AIDS
HIV / AIDS SSF (Round 8), Period 2 | Grant No.: MOL-H-PAS
V1.0
Finance
Programmatic
Management
Select the option you want to see:
Recommendations
Actions
Grant Detail
List of Indicators
Data Entry
Grant Information
Indicators
Reports

## List of Indicators
Dashboard: Moldova - HIV / AIDS
Financial information
Name: | Definition | Measurement | Data Sources
F1: Budget and disbursements by Global Fund | Cumulative budget: Sum of the grant budget from period one (quarter, trimester, or semester) of the current phase, up to and including the dashboard reporting period. Cumulative Disbursments by GF: Sum of all the funds transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to and including the dasboard reporting period. | Currency of the grant ($ or Euro) Cumulative – Figures refer to budget and disbursements for all the periods of the phase up to and including the dashboard reporting period | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F2: Budget and actual expenditures by Grant Objective | Cumulative Budget per Objective: Sum of the grant budget by Objective, from period one of the current phase up to and including the dashboard reporting period. Cumulative Expenditure per Objective: Sum of amounts spent by Objective directly by the PR plus the amounts transferred by the PR to all SRs from the beginning of the phase up to and including dashboard reporting period, by Objective | • Cumulative – Figures refer to budget, disbursements or expenditure for all the periods of the phase up to and including the dashboard reporting period. | PR banking or accounting information; TGF disbursment notification; PU/DR; GF website
F3: Disbursements and expenditures | Disbursement by GF: Prior to this Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), up to but not including dashboard reporting period. Disbursement by GF: Reporting period: Sum of amounts transferred by the GF to either the PR or paid directly to suppliers (e.g. drugs, equipment, bed nets), during dashboard reporting period. PR disbursements and expenditure: Prior to this Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) up to but not including dashboard reporting period. PR disbursements and expenditure: Reporting period: Total funds reported as being spent by the PR and/or disbursed to the Sub Recipients (SRs) during dashboard reporting period. Disbursements to SRs: Prior to this Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), up to but not including dashboard reporting period. Disbursements to SRs:Reporting period: The total amount transferred by the PR to Sub Recipients (SRs), in dashboard reporting period. SR expenditures: Prior to this Reporting period: The sum of all expenditures reported by the SRs, up to but not including dashboard reporting period. SR expenditures: Reporting period: The sum of all expenditures reported by the SRs, during dashboard reporting period. | Currency of the grant ($ or Euro) • Reporting period – Figures refer to budget, disbursements or expenditure for the reporting period to which the dashboard refers. • Prior to reporting period - Figures refer to the total budget, disbursements or expenditure for all the periods before but not including the current period. | PU/DR; PR data: SR reports to PR
F4: Latest PR reporting and disbursement cycle | Days taken to submit final PU/DR to LFA – This indicator measures the number of calendar days it took the PR to send a final Performance Update and Disbursement Request (PU/DR) to the LFA after the end of the period. A 'final' PU/DR would be one for which the LFA did not require any further clarifications from the PR. The expected value is 45 days from the end of the period, as defined in the Grant Agreement. The actual value is the number of calendar days from the end date of the period to the date on which the PR sent to the LFA the final PU/DR. Days taken for disbursement to reach PR – This indicator measures the number of calendar days it took the Global Fund to send the latest disbursement to the PR's account after receipt of the acceptable PU/DR by the LFA. The expected number is 45 days. The actual number is the number of days from the date of transmission by the PR to the LFA of the acceptable PU/DR to the date the disbursement is received by the PR at its bank. Days taken for disbursement to reach SRs – This indicator measures the average number of days for disbursements to be made to all the SRs. The expected value for this indicator will be set locally by the PR and SRs, preferably in the Grant Operations Manual. The actual value is the average of the number of days from the receipt of the funds from the GF by the PR to the date the funds are received by each SR. Different SRs coudl receive funds on different dates and this indicator is the average across all SRs for the latest disbursement. | Number of calendar days; it refers only to reporting period for which the latest disbursement was received and is not cumulative | PR, LFA, GF emails and records; bank notification document or the notice of receipt by the PR to GF; SR reports to PR based on bank records
Management Information
Name: | Definition | Measurement | Data Source
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) | Number of Conditions Precedent (CPs) and Time Bound Actions (TBAs ) fulfilled, or unfulfilled. Within the Unfulfilled category, we distinguish between those CPs and TBAs whose deadline has not passed and those for which the deadline has passed. | Number, cumulative to the dashboard reporting period. Number of fulfilled CPs and/or TBAs plus unfulfilled CPs and/or TBAs should equal the total number set by the Global Fund on the grant | PR records; Grant Performance Reports;
M2: Status of key PR management positions | Number of PR grant management positions planned currently filled or vacant. Full time equivalents of the managerial positions that are on the organizational chart (or otherwise planned) and directly responsible for ensuring grant implementation at the PR, and lead SRs (if necessary). This will include new hires, current staff who are assigned to work on the grant’s management, as well as any staff seconded from other divisions or partner organizations. | Number, in current reporting period | PR records
M3: Contractual arrangements (SRs) | Identified: Total number of potential SRs identified by the PR for the phase. Assessed: Total number of potential SRs assessed by the PR to determine whether they qualify to function as SRs for the grant. Approved: Total number of SRs that have been approved. Signed: Total number of SRs that have signed agreements/contracts with the PR under the grant. Receiving funding: Total number of SRs that are getting funds and/or supplies from the PR. Numbers of SRs Identified, Assessed, Approved, Signed and Receiving funds are cumulative for the phase, with the following exceptions: If an SR does not need new approval in Phase II, then approval in Phase I is counted. If an SR was signed in a previous Phase but is not working in the current Phase, that SR is no longer counted in Identified, Assessed, Approved. | Number, cumulative to the reporting period. A SR is an institution or program with its own workplan, budget and performance targets. | PR records; Sub-agreements/MOUs; CCM records
M4: Number of complete reports received on time | The total number of periodic reports with up-to-date financial, management and performance (programmatic) data received by the PR from SRs and by SRs from the SubSRs (SSRs) by the expected date. A 'complete' report is one that contains all the data that the PR requires for the PU/DR. The expected date would be set by the PR in the sub-agreements. | Number of reports received. The figure reflects only the period of reporting; it is not cumulative. | PR and SR records
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals | This indicator measures the budget approved for the current phase of the grant for purchase of health products and equipment and pharmaceuticals and medicines (categories 4 and 5 in the new Enhanced Financial Report), and the cumulative amounts of financial obligations and expenditures up to the dashboard reporting period. Budget approved: Total approved budget for purchases (categories 4 and 5) for the entire phase of the grant. It does not include the amounts for fees, management, operational costs, etc. Cumulative Obligations: Total of all order(s) placed and monies committed for these purchases by the PR up to and including the dashboard reporting period. Ideally, by the end of the Phase, budget should equal obligations. Cumulative expenditure: Total of actual Expenditures on category 4 and 5 up to and including the dashboard reporting period (whether paid by PR or authorized to be paid by another entity like GF or other). | Currency of the grant ($ or Euro) | Grant agreement approved budget (for categories 4 and 5 of Enhanced Finance Reporting in current phase); and PR financial data (for expenditures), and/or PSM unit (for orders placed and funding committed or obligated).
Note: Category 6 of the EFR will not be considered as part of the budget for pharmaceuticals. Category 6 has several expenditures that are difficult to disaggregate or quantify, such as warehousing costs, distribution costs (particularly when distibution is done by MOHs), and others that are related to operational costs of the PSM component.
M6: Difference between current and safety stock | This indicator is a snapshot of the difference between the current (or last month) stock level of a specific product (medicine in single, fixed-dose combination, bednets, diagnostic kits, etc.) of a particular dose, expressed in monthly needs (number of months of treatment available) for all patients in the program, and the safety or buffer stock (also expressed in months) as established by the disease program, warehouse system or essential drugs program, for the particular product and dosage. The table will show the difference in months in colors: • RED: when the difference is negative or 0, showing that months of existing stock are lower than or equal to what has been established as months of safety stock • YELLOW: when we have more than the level of safety stock (>0) but less than 3 months (+3). • GREEN: when the difference is between 3 and 18 months. • VIOLET: When the difference shows that the level above the safety stock is greater than or equal to 18 months indicating a potential overstock) problem. For a full description of how this indicator is calculated, please see the User’s Manual. | Number of months | PR records: Warehouse data.
Programmatic Indicators (from Performance Framework)
Indicator | Definition (from M&E Plan, September 2009) | Measurement | Data Source
Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS | Indicator refers to training of ART and MDT medical specialists, infectious diseases and PHC specialists, social assistants and MDT non-medical specialists. This is a composite indicator, related activities: 3.1.1., 3.1.2., 3.1.4. & 3.1.5 | A person is considered trained if he/she has attended the course not less than 80% and signed the list of participation at training (people signed the list of attendance twice a day along the course). | Training records (daily attendance lists signed by trainees)
Number of PLHIV receiving food parcels to improve ARV treatment adherence | Patients on ART treatment will receive quarterly incentives (food parcels) for better adherence to treatment, in both civilian and penitentiary sectors. A PLHIV is considered "reached" if s/he has received a food package per quarter at least one quarter. Quarterly will be distributed 800 food parcels based on the socio-economic vulnerability criteria. Targets for this indicator are annual and have been calculated based on an estimated quarterly increase by 10% in the number of new beneficiaries. Related activity: 4.1.1 | New persons who received a food package per quarter at least quart. | Register of people reached and SR program reports
Number of people living with HIV/AIDS reached with care and support services | The beneficiaries are provided with the following services: psycho-social counseling and support, medical counseling and refferal, distribution of information materials, peer counseling, self-support groups and food support, etc. The beneficiary is considered "reached" if s/he has received at least one of the listed services. Related activity 4.1.2,4.1.3 & 4.4.1-4.4.3. Target include baseline. | The beneficiaries are provided with the following services: psycho-social counseling and support, medical counseling and referral, distribution of information materials and peer counseling. The beneficiary is considered "reached" if he/she has received at least one of the listed services. | Register of people reached and SR program reports
Number of children infected and affected by HIV/AIDS who receive social support | The social support includes food parcels and clothing and school supplies for HIV infected children and food support for children born from HIV positive mothers with unknown status. Quarterly will be distributed 230 food parcels. Targets for this indicator are annual and have been calculated based on an estimated quarterly increase by 10% in number of new born to HIV positive mothers. It is a composite indicator, related activities: 4.3.1.& 4.3.2. | A child is considered "reached" if she/he has received a social support (food parcels and clothing and school supplies for HIV infected children and food support for children born from HIV positive mothers with unknown status) per quarter at least quart. | Register of people reached and SR program reports
Number of Injecting drug users on oppoid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation | The beneficiary is considered "reached" if s/he has received at least three of the services listed (psycho-social support, self-support groups, peer to peer education, distributions of information materials, food support,etc.). Related activity 4.2.1-4.2.3 Target include baseline. | The beneficiary is considered "reached" if he/she has received at least three of the services listed (psycho-social support, self-support groups, peer to peer education, distributions of information materials, food support, etc.). | Register of people reached and SR program reports
Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months | Numerator: number of individuals completing at least 6 months of continuous treatment on OST that initiated treatment 6-12 months prior to the end of the reporting period. Denominator: total number of individuals that initiated treatment 6-12 months prior to the end of reporting period. The indicator is linked to percentage and absolute numbers will be provided when reporting results. The targets refer to the patient cohort (both new and repeated cases) that initiated treatment in the first 6 months of the last 12 months period. NOTE: PAS Center is responsible for data collection and validation. | Determine the number of people who initiated OST (first or repeated) in the first six months of the last 12 months and evaluated how many of these people remained in OST at least 6 months continuously. 6 months cohort based evaluations. | OST centers administrative records (RND, Balti municipal hospital and DPI)
Number of human rights strategic litigation cases for PLHIV initiated | Indicator refers to cases of PLHIV rights violation initiated for strategic litigation in order to change the existing practices. Related activity 5.2.2-5.2.4 | Total number of human rights strategic litigation cases registered in the register | List of human rights strategic litigation cases
Number of PLHIV assisted by legal aid (consultancies offered by legal network) | The indicator refers to legal assistance provided remotely to PLHIV on issues of legal, civil (including disclosure of HIV status), administrative nature. Related activity 5.2.1&5.2.4 | Person is considered "reached" if he/she receives at least one consultation offered by legal network. | List of PLHIV assisted by legal aid
Number of members of the civil society trained in services provision to PLHIV | Indicator refers to training of members of the civil society in services provision to PLHIV. Related activities: 5.3.9. | A person is considered trained if he/she has attended the course not less than 80% and signed the list of participation at training (people signed the list of attendance twice a day along the course). | Training records (daily attendance lists signed by trainees)
Indicator Number: Name (Perf Framework No.) | Definition | Measurement | Data Source
The indicators should be selected by the PRs and members of the CCM or the CCM Technical Committee, from the Performance Framework |  |  | Performance Framework
Menu

## Data Entry
Grant information
| Country: | Moldova |  | Title of the Grant: |  | Reducing HIV-related burden in the Republic of Moldova
| Grant No.: | MOL-H-PAS |  | Component: |  | HIV / AIDS | Total Funding: | EUR 12057410
| Principal Recipient: | PAS Center |  |  | Round: | SSF (Round 8) | Phase: | Period 2
| Start Date (dd/Mmm/yy): | January 01, 2010 |  | Local Fund Agent: |  | PwC (PricewaterhouseCoopers)
| Latest Rating: | A2 |  | Fund Portfolio Manager: |  | Tatiana Vinichenko
Information reporting period
| Report Period: | P8 | From: | July 01, 2013 | To: | December 31, 2013 | Date of entry of information: |  | March 10, 2014
| Prepared by: |  | PAS Center
Information on indicators
Enter the data based on the colour-coded cells
| Financial Information: |  | Management Information: |  |  | Programmatic Information:
| Financial Information: | [8 empty] | Enter finance data in every orange cell like this.
| Currency of the grant |  | €
F1: Budget and disbursements by Global Fund
| Disbursement | [15 empty] | 0
| Reporting period |  |  |  | P1-P12 (Q1.2010-Q4.2012) | P13 (Q1.2013) | P14 (Q2.2013) | P15 (Q2.2013) | P16 (Q2.2013) |  |  |  |  | % Cumulative |  |  | 0
| Budget (in €) |  |  |  | 8116137 | 470112.82 | 506932.17 | 498482.07 | 511009.03 |  |  |  |  | 104.6% |  |  | 0
| Disbursements by GF (in €) |  |  |  | 8116137 | 2449445.91 | [10 empty] | 8116137
| Cumulative budget |  |  |  | 8116137 | 8586249.82 | 9093181.99 | 9591664.06 | 10102673.09 | [7 empty] | 8586249.82
| Cumulative disbursements |  |  |  | 8116137 | 10565582.91 | 10565582.91 | 10565582.91 | 10565582.91 | [7 empty] | 9093181.99
|  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% |  |  |  | 9591664.06
F2: Budget and actual expenditures by Grant Objective
| Grant Objective | Cumulative Budget (in €) | Cumulative Expenditures (in €)
| Develop capacity and ensure program sustainability | 1132167.45 | 1123553.7092
| Support PLHIV, PWID and ensure institutionalization | 6446522.94 | 6478562.516
| Ensure engagement of civil society and key affected population and promote human rights | 959092.28 | 937070.444
| Planning and administration | 1564890.42 | 1620362.0591
| Total | 10102673.09 | 10159548.7283 |  | OK: Data match
| F3: Disbursements and expenditures | [15 empty] | 10102673.09
0
|  | Prior to reporting period | Current reporting period | Total Spent and Disbursement (in €) | [11 empty] | 0
| Disbursed by Global Fund | 10565582.91 |  | 10565582.91
| PR expenditure and disbursement | 9166901.1 | 992657.25 | 10159558.35
| Disbursed to SRs | 5465034.68 | 489889 | 5954923.68
| SR expenditures | 5419427.21 | 479098 | 5898525.21
F4: Latest PR reporting and disbursement cycle
Last fund disbursement: Number of calendar days
|  | Expected (days) | Actual (days)
| Days taken to submit final PU/DR to LFA | 45 | 42
| Days taken for disbursement to reach PR | 45 | 83
| Days taken for disbursement to reach SRs | 20 | 5
| Management Information: | [5 empty] | Enter management data in every blue cell.
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs)
|  |  | Fulfilled | Not fulfilled, but within deadline | Not fulfilled, and past the deadline | Total
| Conditions precedent (CPs) |  | 2 |  |  | 2
| Time Bound Actions (TBAs) |  |  |  |  | 0
M2: Status of key PR management positions
|  | Planned | Filled | Vacant
| PMU | 14 | 14 | 0
M3: Contractual arrangements (SRs)
|  | Identified | Assessed | Approved | Signed | Receiving Funding
| SRs | 4 | 4 | 4 | 2 | 2
M4: Number of complete reports received on time
|  | # Expected | # Received | Pending
| SSR to SR | 19 | 18 | 1
| SRs to PR | 2 | 2 | 0
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals
|  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
Budget Approved*
Obligations
Expenditures
| Budget Approved cumulative* | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Obligations cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Expenditures cumulative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
M6: Difference between current and safety stock
| Component | Products | (1) Number of tablets per patient per day (Review country treatment guidelines) | (2 = 1 x 30) Monthly treatment (Tablets per patient x 30 days) | (3) Total patients in treatment | (4 = 2 x 3) Total # tab/pills required for all patients per month | (5) Current stock in central warehouse (that does not expire within the next 3 months) | (6 = 5 / 4) Stock level expressed in months of treatment for all current patients | (7) Level of safety stock (expressed in months and defined by country) | (8 = 6 - 7) Difference between current stock and safety stock
| HIV / AIDS | P1: Please Select
Please Select
Please Select
Please Select
| Programmatic Information: | P9: Enter performance data in every yellow cell.
| Programmatic indicators (Performance Framework ) |  |  | Code | Directly Tied? |  | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P14 |  | P15 | P16
TOP 3 | Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV/SIDA şi au primit suport social) |  |  | 4.2 | Yes | Target | 3250 | 3500 | 3750 | 4000 | 4375 | 4750 | 4832 | 5207 | 5357 | 5507 | 5657 | 5807 | 5947 | 6087 |  | 6227 | 6367
[6 empty] | Achieved | 2093 | 2817 | 3197 | 3717 | 3976 | 4296 | 4564 | 4853 | 5107 | 5327 | 5519 | 5704 | 5874 | 6085 |  | 6262 | 6444
| Number of children infected and affected by HIV/AIDS who receive social support (Numărul de copii infectaţi şi afectaţi de HIV/SIDA care primesc suport social) |  |  | 4.3 | Yes | Target | 95 | 125 | 155 | 185 | 216 | 248 | 352 | 372 | 392 | 412 | 432 | 452 | 230 | 244 |  | 258 | 272
[6 empty] | Achieved | 91 | 133 | 195 | 236 | 298 | 332 | 363 | 395 | 395 | 462 | 482 | 509 | 229 | 264 |  | 297 | 325
| Number of Injecting drug users on opioid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de CDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea CDI) |  |  | 4.4 | Yes | Target | 54 | 108 | 162 | 216 | 280 | 344 | 407 | 471 | 511 | 551 | 591 | 631 | 651 | 671 |  | 691 | 711
[6 empty] | Achieved | 61 | 131 | 180 | 225 | 284 | 322 | 368 | 437 | 462 | 481 | 500 | 534 | 554 | 579 |  | 592 | 632
| Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS (Numărul personalului medical (medici şi asistente medicale) şi non-medical (psihologi, asistenţi sociali, educatori de la egal la egal) instruiţi în HIV/SIDA) |  |  | 3.1 | Yes | Target | 25 | 150 | 225 | 400 | 500 | 625 | 1224 | 1410 | 1510 | 1610 | 1710 | 1810 | 50 | 90 |  | 90 | 90
[6 empty] | Achieved | 50 | 174 | 268 | 594 | 788 | 1099 | 1224 | 1395 | 1448 | 1608 | 1804 | 1898 | 24 | 129 |  | 86 | 86
| Number of PLHIV receiving food parcels to improve ARV treatment adherence (Numărul de PTH care primesc pachete alimentare pentru a îmbunătăți aderenţa la tratamentul ARV) |  |  | 4.1 | Yes | Target | 108 | 216 | 324 | 432 | 573 | 715 | 1011 | 1061 | 1101 | 1141 | 1181 | 1221 | 800 | 880 |  | 960 | 1040
[6 empty] | Achieved | 108 | 269 | 462 | 588 | 803 | 961 | 1134 | 1257 | 1257 | 1452 | 1554 | 1611 | 800 | 842 |  | 890 | 948
| Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months (Numărul şi procentul persoanelor aflate în tratamentul de substituție cu metadonă (TSO) care au fost în TSO continuu cel puțin 6 luni pe parcursul ultimelor 12 luni) |  |  | 4.5 |  | Target | n/a | n/a | n/a | n/a | n/a | 50% | n/a | 55% | n/a | 57% | n/a | 59% | n/a | 60% |  | n/a | 60%
[6 empty] | Achieved | n/a | n/a | n/a | n/a | n/a | 53.18% | n/a | 56.04% | n/a | 57.85% | n/a | 42.68% | n/a | 44.61% |  | n/a | 47%
| Number of human rights strategic litigation cases for PLWH initiated (Numărul de cazuri de încălcare a drepturilor PTH inițiate pentru litigare strategică) |  |  | 5.1 | Yes | Target | 5 | 10 | 15 | 20 | 25 | 30 | 35 | 40 | 45 | 50 | 55 | 60 | 5 | 10 |  | 5 | 10
[6 empty] | Achieved | 8 | 15 | 24 | 29 | 34 | 39 | 44 | 50 | 55 | 60 | 65 | 70 | 5 | 11 |  | 5 | 10
| Number of PLHIV assisted by legal aid (consultancies offered by legal network) (Numărul de PTH care au beneficiat de asistență juridică) |  |  | 5.2 | Yes | Target | 10 | 20 | 30 | 40 | 55 | 70 | 212 | 242 | 272 | 302 | 332 | 362 | 35 | 70 |  | 35 | 70
[6 empty] | Achieved | 25 | 78 | 108 | 142 | 163 | 182 | 210 | 251 | 296 | 344 | 394 | 429 | 52 | 104 |  | 57 | 114
| Number of members of the civil society trained in services provision to PLHIV (Numărul de membri ai societăţii civile instruiţi în furnizarea de servicii pentru PTH) |  |  | 5.3 | Yes | Target | 35 | 70 | 105 | 140 | 190 | 240 | 390 | 440 | 490 | 540 | 590 | 640 | 0 | 25 |  | 25 | 50
[6 empty] | Achieved |  | 78 |  |  |  | 340 | 411 | 542 | 608 | 712 | 741 | 780 | 0 | 30 |  | 27 | 54
| Table is automatically updated. No data or information is to be entered here. |  |  | Code | Directly Tied? |  | 0 | 0 | 0 | P1-P12 (Q1.2010-Q4.2012) | P13 (Q1.2013) | P14 (Q2.2013) | P15 (Q2.2013) | P16 (Q2.2013) | 0 | 0 | 0 | 0 | P13 | P14 | 0 | P15 | P16
| Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV/SIDA şi au primit suport social) |  |  | 4.2 | Yes | Target | 3250 | 3500 | 3750 | 4000 | 4375 | 4750 | 4832 | 5207 | 5357 | 5507 | 5657 | 5807 | 5947 | 6087 | 0 | 6227 | 6367
[6 empty] | Achieved | 2093 | 2817 | 3197 | 3717 | 3976 | 4296 | 4564 | 4853 | 5107 | 5327 | 5519 | 5704 | 5874 | 6085 | 0 | 6262 | 6444
| Number of children infected and affected by HIV/AIDS who receive social support (Numărul de copii infectaţi şi afectaţi de HIV/SIDA care primesc suport social) |  |  | 4.3 | Yes | Target | 95 | 125 | 155 | 185 | 216 | 248 | 352 | 372 | 392 | 412 | 432 | 452 | 230 | 244 | 0 | 258 | 272
[6 empty] | Achieved | 91 | 133 | 195 | 236 | 298 | 332 | 363 | 395 | 395 | 462 | 482 | 509 | 229 | 264 | 0 | 297 | 325
| Number of Injecting drug users on opioid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de CDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea CDI) |  |  | 4.4 | Yes | Target | 54 | 108 | 162 | 216 | 280 | 344 | 407 | 471 | 511 | 551 | 591 | 631 | 651 | 671 | 0 | 691 | 711
[6 empty] | Achieved | 61 | 131 | 180 | 225 | 284 | 322 | 368 | 437 | 462 | 481 | 500 | 534 | 554 | 579 | 0 | 592 | 632
Note on B68: If data are not available, do not enter zeros; rather, leave the cells in the table blank.
Note on B69: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Note on B30: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B90: To define your periods (eg. P1, P2, P3 etc or P9, P10, P11 etc) you need to unprotect the cells.
Note on B75: If data are not available, do not enter zeros; rather, leave the cells in this table blank.
Menu

## Grant Detail
Dashboard: Moldova - HIV / AIDS
Country: | Moldova |  | Title of the Grant: |  | Reducing HIV-related burden in the Republic of Moldova
Component: | HIV / AIDS | Grant No. | MOL-H-PAS | Start Date: |  | January 01, 2010 | Total Funding | EUR 12057410
Round: | SSF (Round 8) | Phase: | Period 2 | Principal Recipient: |  | PAS Center
Report Period: | P8 | from: | July 01, 2013 | to: |  | December 31, 2013 | Latest Rating: | A2
Local Fund Agent: | PwC (PricewaterhouseCoopers) |  |  | Fund Portfolio Manager: |  | Tatiana Vinichenko
Prepared by: | PAS Center |  |  | Report preparation date: |  | March 10, 2014
http://www.crwflags.com/fotw/flags/country.html
Menu

## Finance
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Period 2 |  |  |  | Report Period: |  | P8
Latest Rating: | A2 |  | PAS Center |  | From: |  | July 01, 2013
|  | Reducing HIV-related burden in the Republic of Moldova |  |  |  | To: | December 31, 2013
Financial Indicators
F1: Budget and disbursements by Global Fund - in (€) Report Period: P8 |  |  |  | F3: Disbursements and expenditures - in (€) Report Period: P8
Comments: | By December 31, 2013, the total amount disbursed by TGF to PAS Center was EUR 10,565,583. The cumulative disbursement rate is 104.6%. The variance is due to the fact that the cumulative disbursement includes the buffer for Q1, 2014 in a total amount of EUR 465,363. (Până la 31 decembrie 2013, Centrului PAS i-au fost disbursate de către Fondul Global 10,565,583 Euro. Rata cumulativă a disbursării este de 104.6%. Variația este cauzată de faptul că disbursarea cumulativă include un buffer pentru Tr.1, 2014 în valoare totală de 465,363 Euro.) |  |  | Comments: | The cash outflow rate for the reporting period is 98.3% (actual: EUR 992,657, budget: EUR 1,009,491) of the semi-annual budget and the cumulative cash outflow as of December 31, 2013 is 100.56% (actual: EUR 10,159,549, budget: EUR 10,102,673). The cumulative variance mainly consist of payments afferent to commitments from Period 1, payments the NGO "Youth for the Wright to Live" from year 2014 budget as per TGF approval dated February 20, 2013 for the renovation, and commitments that will be paid over next semester. (Rata de absorbţie pentru perioada raportată este de 98.3% (Actual 992,657 Euro/Budget 1,009,491 Euro) din bugetul semianual şi rata cumulativă de absorbţie din buget la 31.12.2013 este 100.56% (actual: 10,159,549 Euro, budget: 10,102,673 Euro). Variația cumulativă se datorează în mare parte plăţilor aferente Perioadei 1, plăților din bugetul anului 2014 către ONG-ul "Tinerii pentru Dreptul la Viață" pentru renovare conform aprobării FG din data de 20 februarie 2013 și angajamentelor care vor fi plătite pe parcursul semestrului următor.)
F2: Budget and actual expenditures by Grant Objective - in (€) Report Period: P8 |  |  |  | F4: Latest PR reporting and disbursement cycle Report Period: P8
Comments: | The cumulative cash outflow rate as of December 31, 2013 per Objectives range between 98% and 104% the variances being due to payments afferent to commitments from Period 1, advanced payments from year 2014 budget and commitments that will be paid over next semester. (Rata cumulativă de absorbţie din buget la 31.12.2013 per Obiective este între 98% şi 104% variaţia datorînduse în mare parte plăţilor aferente Perioadei 1, plăților în avans din bugetul anului 2014 și angajamentelor care vor fi plătite pe parcursul semestrului următor.) |  |  | Comments: | The PU for Semester 2, 2013 has been submitted to LFA in due terms (42 days after the end of reported period), on February 11, 2014. The disbursement requested with the previous PU/DR for S2, 2012 (submitted on February 15, 2013) reached the PR on 08 May, 2013 (83 days after the PU/DR) and include the budget for semester 2, 2013 and the buffer for Q1, 2014. (Actualizarea progresului pentru Semestrul 2, 2013 a fost remisa Agentului Local al Fondului in termenii stabiliți (42 de zile după finisarea perioadei raportate) pe data de 11 februarie 2013. Disbursarea solicitată cu precedenta Actualizare de progres (PU/DR) pentru Semestrul 2, 2012 a fost primită de PR pe data de 08 mai 2013 (83 zile de la PU/DR). Disbursarea include bugetul pentru semestrul 2, 2013 și un buffer pentru Tr.1, 2014.)
Last fund disbursement: Calendar days
[6 empty] | Expected (days) | Actual (days)
|  |  |  | Days taken to submit final PU/DR to LFA |  | 45 | 42
|  |  |  | Days taken for disbursement to reach PR |  | 45 | 83
|  |  |  | Days taken for disbursement to reach SRs |  | 20 | 5
Menu

## Management
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Period 2 |  |  |  |  | Report Period: |  | P8
Latest Rating: | A2 |  | PAS Center |  |  | From: |  | July 01, 2013
|  | Reducing HIV-related burden in the Republic of Moldova |  |  |  |  | To: | December 31, 2013
Management Indicators
M1: Status of Conditions Precedent (CPs) and Time Bound Actions (TBAs) Report Period: P8 |  |  |  | M2: Status of key PR management positions Report Period: P8
Comments: | The two special conditions afferent to Period 2 have been fulfilled in strict accordance with their provisions. (Cele două condiții speciale aferente Perioadei 2 au fost îndeplinite, în strictă conformitate cu prevederile contractuale.) |  |  | Comments: | Two full time positions and 12 part time. (Două poziţii cu normă plină şi 12 - parţială.)
M3: Contractual arrangements (SRs) Report Period: P8 |  |  |  | M4: Number of complete reports received on time Report Period: P8
Comments: | Four Sub-recipients (SRs) have been identified initialy (2010) to implement different components within the program: Soros Foundation-Moldova (SFM); League of people living with HIV of Moldova; New Life, Moldovan Institute for Human Rights. One SR (SFM) has been earlier assessed by the governmental PR of GF grants as it acts as an SR since GF Round one. Two other SRs have been assessed (New Life and Moldovan Institute for Human Rights) by PAS Center the last one (League of people living with HIV of Moldova) by TGF Local Fund Agent. Four sub-grant agreements have been signe following the assessment. In September 2011, due to lack of capacity for adequate implementation of the grant portion contracted the sub-grant agreement with one of the SRs (League of people living with HIV) was terminated and the management of activities has been entrusted to an other SR ( SFM). Respectively three sub-recipients continued to receive funds till the end of Period one (December 31, 2012). During renewal one SR component has been reorganised and starting with Period two (2013) there are two SRs that receiv funds within the grant. (Patru Sub-Recipienţi (SR), au fost identificaţi inițial (2010) pentru a implementa diferite componente în cadrul programului: Fundația Soros-Moldova (FSM), Liga persoanelor care trăiesc cu HIV din Moldova, Viaţa Nouă, Institutul pentru Drepturile Omului din Moldova. Un SR (SFM) a fost evaluat anterior de către RP guvernamental, deoarece activează în calitate de SR începănd cu Runda 1. Alţi doi SR au fost evaluaţi (Viaţa Nouă și Institutul pentru Drepturile Omului din Moldova) de către Centrul PAS iar ultimul (Liga persoanelor care trăiesc cu HIV din Republica Moldova) de către Agentul Local al Fondului Global. Urmare a evaluării au fost semnate patru acorduri de sub-grant. În septembrie 2011, din cauza lipsei capacității de implementare adecvată a componentului de grant contractat, acordul de sub-finantare cu unul dintre SR (Liga persoanelor care trăiesc cu HIV) a fost reziliat și gestionarea activităților a fost încredințată altui SR (SFM). Respectiv trei SR au primit fonduri până la finele Perioadei unu (31 decembrie 2012). La etapa de reînoire a grantului, componentul implementat de unul dintre acesti SR a fost reorganizat și începănd cu Perioada 2 (2013) doi SR primesc resurse din cadrul grantului trei SR. |  |  | Comments: | The SRs’ quarterly reports (financial report, activity report and performance framework) are due to the PR not later than 25 days after the close of each quarter and are generally submitted in time. The clearance period vary from one SR to an other subject to the completeness and consistence of the reports. For the SR SFM the Sub-subrecipients financial reports are due quarterly and can be submitted during the following quarter, the activity reports are due not later than 10 days from the end of each month and are generally submitted in time except one Ssr - NGO Master in Public Health – that is constantly late in reporting. During the reporting period reflected in this dashboard 16 reports from 17 due were submited in time. For the SR New Life the reports (financial, activity and indicators) are due not later than 15 days after the close of each quarter and are generally submitted in time. (Rapoartele trimestriale ale SR-ului (raport financiar, raport de activitate și cadrul de performanță) urmează a fi transmise RP nu mai târziu de 25 de zile de la încheierea fiecărui trimestru. Rapoartele sunt de regulă prezentate la timp. Perioada de verificare şi aprobare variază de la un SR la altul în funcţie de exhaustivitatea și consistența rapoartelor. Pentru SR-ul FSM rapoartele financiare ale Sub-subrecipienţilor (Ssr) urmează a fi transmise trimestrial și pot fi prezentate în trimestrul următor, rapoartele de activitate urmează a fi prezentate nu mai târziu de 10 zile de la sfârșitul fiecărei luni și sunt în general prezentate la timp cu excepția unui Ssr - ONG-ul Master în Sănătatea Publică - care întârzie raportarea în mod constant . Pe parcursul perioadei de raportare reflectată în aces raport, 16 raporte din 17 planificate au fost transmise la timp. Pentru SR-ul Viaţa Nouă rapoartele (financiar, de activitate și indicatorii) urmează a fi prezentate nu mai târziu de 15 zile de la încheierea fiecărui trimestru și sunt, de regulă, prezentate la timp.)
M5: Budget and Procurement of health products, health equipment, medicines and pharmaceuticals |  |  |  | M6: Difference between current and safety stock Report Period: P8
Comments: | N/A |  |  | Comments: | N/A
|  |  |  | Component | Products | Stock level expressed in months of treatment for all current patients | Months of safety stock | Difference between current stock and safety stock
|  |  |  | HIV / AIDS | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
[5 empty] | Please Select |  | 0
* Includes only EFR category 4 and 5 (Health products and health equipment & Medicines and Pharmaceuticals)
Menu

## Programmatic
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Period 2 | [8 empty] | Report Period: |  | P8
Latest Rating: | A2 |  | PAS Center | [7 empty] | From: | July 01, 2013
|  | Reducing HIV-related burden in the Republic of Moldova | [8 empty] | To: | December 31, 2013 | [7 empty] | Raiting |  | Valor
Programmatic Indicators
Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV/SIDA şi au primit suport social) |  |  |  | Number of children infected and affected by HIV/AIDS who receive social support (Numărul de copii infectaţi şi afectaţi de HIV/SIDA care primesc suport social) |  |  |  | Number of Injecting drug users on opioid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de CDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea CDI)
Comment: P1 | During S8 a total 359 PLHIV were primarily reached with care and support services through four social regional centers providing assistance to PLHIV and 10 territorial organizations that ensures outreach to PLHIV and their families. The beneficiaries are provided with the following services: psycho-social counseling and support, medical counseling and referral, distribution of information materials, peer counseling, self-support groups and food support, etc. The indicator is achieved. (Pe parcursul semestrului 8, un total de 359 PTH au fost primar acoperiți cu servicii de îngrijire şi suport prestate în cadrul celor patru Centre Sociale Regionale şi a 10 organizații teritoriale care prestează servicii direct PTH și membrilor familiilor lor. Beneficiarilor le sunt prestate următoarele servicii: suport și consiliere psiho-socială, consiliere medicală și referiri, diseminarea materialelor informaționale şi consiliere de la egal la egal, grupuri de ajutor reciproc și suport alimentar, etc. Indicatorul este atins.) |  |  | Comment: P2 | A total of 325 children (109 infected and 216 affected by HIV) received social support during year 2013 (primarily reached), out of them 61 (13 infected and 48 affected by HIV) primarily reached during S8. Each quarter 230 children (all HIV infected children that can be reached and the majority of children born from HIV infected mother with unknown status) benefit of food parcels. At the same time each semester HIV positive children benefit of a set of stationary and clothing for school as part of social support program. During reported period the number of HIV positive children that benefited of clothing and school supplies was 109, exceeding by 14 the planned number of 95. This fact has determined the need to reallocate additional budget (from savings under other budget lines targeted at PLHIV support) in order to cover fourteen additional sets of clothing and school supplies. The indicator is overachieved. Reason for variance: The number of children primarily reached with social support is determined by the number of children diagnosed with HIV that are reached and by the number of children born from HIV positive mothers immediately before and during the reported period. During reported period the number of HIV positive children reached was 109, exceeding by fourteen the planned number of 95. Note: In Peroada 1 the targets were cumulative over program term, but starting with Period 2 - the targets are cumulative annually. (Un total de 325 copii (109 copii HIV infectați și 216 copii afectați de HIV) au beneficiat de suport social pe parcursul anului 2013 (acoperiți primar), dintre care 61 (13 infectati și 48 afectati de HIV) primari acoperiti in S8. În același timp, în fiecare trimestru, 230 copii (toți copiii infectați cu HIV, care pot fi acoperiți cu servicii, și majoritatea copiilor născuți din mame HIV pozitive) beneficiază semestrial de un set de haine şi rechizite școlare ca parte a programului de acordare a suportului social. Pe parcursul perioadei de raportare, numărul de copii HIV infectați care au primit cîte un set de haine şi rechizite școlare a crescut la 109, depășind cu 14 unități numărul planificat de 95. Acest fapt a determinat necesitatea realocării unui buget adițional (din economiile obținute în cadrul altor linii bugetare orientate către suportul PTH) pentru a acoperi patrusprezece seturi suplimentare de îmbrăcăminte şi rechizite școlare. Indicatorul este depășit. Cauza variației: Numărul de copii primar acoperiți cu suport social este determinat de numărul de copii diagnosticați cu HIV și numărul copiilor născuți din mame HIV pozitive imediat înainte și în perioada de raportate. Pe parcursul perioadei de raportare numarul copiilor HIV pozitivi acoperiți cu servicii a fost 109, depasit cu 14 numarul planificat de 95.) Notă: În Peroada 1, tintele erau cumulative pe durata programului, iar începînd cu Perioada 2 - tintele sunt cumulative anual. |  |  | Comment: P3 | During S8 a total of 53 PWIDs on opioid substitution therapy (primarily reached) received at least 3 support services from the package (psycho-social support, self-support groups, peer to peer education, distributions of information materials, food support, etc.) offered by NGOs working in PWUDs rehabilitation. The number of PWIDs on OST covered with psycho-social support is directly dependent to the number of PWIDs enrolled in OST treatment (new patients) which is continuously decreasing. During S2, 2013, 50 new clients were enrolled in the substitution therapy program, the number of OST patients covered with support services (primarily reached) being 53 versus 40 planned. The indicator is achieved in proportion of 89%. Reason for variance: The target for the period 8 (40 persons primarily reached) has been exceeded (53 people reached). The underachievement of the cumulative target for the reported period (over program term) is determined by the variation between targets settled and results registered for period one of grant implementation caused by continuously decreasing enrolment of new patients in OST. As the number of OST patients that can be covered with psycho-support services is directly tied to new patients enrolled in OST, the enrolment dynamics in period one has determined and directly impacted the achievement of targets for this indicator and is affecting the results for the reported period as the target is cumulative over program term. (Pe parcursul semestrului 8 un total de 53 CDI aflați în terapia de substituție cu metadonă (primar acoperiți) au primit cel puțin 3 servicii de suport din pachetul serviciilor (suport psiho-social, grupuri de ajutor reciproc, educație de la egal la egal, diseminarea materialelor informaționale, suport alimentar) oferite în cadrul centrelor de zi de către ONG-urile care lucrează în domeniul reabilitării CDI. Numărul de CDI aflați în TSO, acoperiți cu suport psiho-social este direct dependent de numărul CDI înrolați în TSO (cazuri noi), cifra care este în continuă scădere. Pe parcursul S2, 2013, 50 beneficiari noi au fost înrolați în terapia de substituție, numărul de pacienți în TSO acoperiți cu servicii de suport (primari acoperiți) fiind de 53 față de 40 planificați. Indicatorul este atins în proporție de 89%. Cauza variației: Ținta pentru perioada 8 (40 persoane noi primar acoperite) a fost depășită (53 persoane acoperite). Neatingerea țintei cumulative pentru perioada raportată (pe toata perioada grantului) este determinată de variația între țintele stabilite și rezultatele înregistrate pentru perioada întâi de implementare a grantului cauzată de scăderea continua a pacienților înrolați în TSO. Numărul de pacienți în TSO care pot fi acoperiți cu servicii de suport psiho-social este direct proporțional cu numărul pacienților noi înrolați în TSO, dinamica înrolării în perioada întâi a determinat și a afectat direct atingerea țintei pentru acest indicator și afectează rezultatul pentru perioada raportată deoarece ținta propusă se calculează cumulativ pentru toată perioada grantului.)
Indicators |  |  | Target (cumulative over program term) | Achieved (cumulative over program term) | 0% - 59% | 60% - 89% | > 90% | Comments |  |  |  |  | min | 0 | 30% | 60% | 90% | 100% |  | min | 0 | 20% | 40% | 60% | 80%
Number of people living with HIV/AIDS reached with care and support services (Numărul persoanelor care trăiesc cu HIV/SIDA şi au primit suport social) |  |  | 6367 | 6444 | 101.2% |  |  | During S8 a total 359 PLHIV were primarily reached with care and support services through four social regional centers providing assistance to PLHIV and 10 territorial organizations that ensures outreach to PLHIV and their families. The beneficiaries are provided with the following services: psycho-social counseling and support, medical counseling and referral, distribution of information materials, peer counseling, self-support groups and food support, etc. The indicator is achieved. (Pe parcursul semestrului 8, un total de 359 PTH au fost primar acoperiți cu servicii de îngrijire şi suport prestate în cadrul celor patru Centre Sociale Regionale şi a 10 organizații teritoriale care prestează servicii direct PTH și membrilor familiilor lor. Beneficiarilor le sunt prestate următoarele servicii: suport și consiliere psiho-socială, consiliere medicală și referiri, diseminarea materialelor informaționale şi consiliere de la egal la egal, grupuri de ajutor reciproc și suport alimentar, etc. Indicatorul este atins.) |  |  |  |  | max | 30% | 60% | 90% | 100% | 200% |  | max | 20% | 40% | 60% | 80% | 100%
Number of children infected and affected by HIV/AIDS who receive social support (Numărul de copii infectaţi şi afectaţi de HIV/SIDA care primesc suport social) |  |  | 272 | 325 | 119.5% |  |  | A total of 325 children (109 infected and 216 affected by HIV) received social support during year 2013 (primarily reached), out of them 61 (13 infected and 48 affected by HIV) primarily reached during S8. Each quarter 230 children (all HIV infected children that can be reached and the majority of children born from HIV infected mother with unknown status) benefit of food parcels. At the same time each semester HIV positive children benefit of a set of stationary and clothing for school as part of social support program. During reported period the number of HIV positive children that benefited of clothing and school supplies was 109, exceeding by 14 the planned number of 95. This fact has determined the need to reallocate additional budget (from savings under other budget lines targeted at PLHIV support) in order to cover fourteen additional sets of clothing and school supplies. The indicator is overachieved. Reason for variance: The number of children primarily reached with social support is determined by the number of children diagnosed with HIV that are reached and by the number of children born from HIV positive mothers immediately before and during the reported period. During reported period the number of HIV positive children reached was 109, exceeding by fourteen the planned number of 95. Note: In Peroada 1 the targets were cumulative over program term, but starting with Period 2 - the targets are cumulative annually. (Un total de 325 copii (109 copii HIV infectați și 216 copii afectați de HIV) au beneficiat de suport social pe parcursul anului 2013 (acoperiți primar), dintre care 61 (13 infectati și 48 afectati de HIV) primari acoperiti in S8. În același timp, în fiecare trimestru, 230 copii (toți copiii infectați cu HIV, care pot fi acoperiți cu servicii, și majoritatea copiilor născuți din mame HIV pozitive) beneficiază semestrial de un set de haine şi rechizite școlare ca parte a programului de acordare a suportului social. Pe parcursul perioadei de raportare, numărul de copii HIV infectați care au primit cîte un set de haine şi rechizite școlare a crescut la 109, depășind cu 14 unități numărul planificat de 95. Acest fapt a determinat necesitatea realocării unui buget adițional (din economiile obținute în cadrul altor linii bugetare orientate către suportul PTH) pentru a acoperi patrusprezece seturi suplimentare de îmbrăcăminte şi rechizite școlare. Indicatorul este depășit. Cauza variației: Numărul de copii primar acoperiți cu suport social este determinat de numărul de copii diagnosticați cu HIV și numărul copiilor născuți din mame HIV pozitive imediat înainte și în perioada de raportate. Pe parcursul perioadei de raportare numarul copiilor HIV pozitivi acoperiți cu servicii a fost 109, depasit cu 14 numarul planificat de 95.) Notă: În Peroada 1, tintele erau cumulative pe durata programului, iar începînd cu Perioada 2 - tintele sunt cumulative anual. | [5 empty] | de 0 a 0.3 | de 0.3 a 0.6 | de 0.6 a 0.9 | de 0.9 a 1 | de 1 a 2 | Rating | Valor | de 0 a 0.2 | de 0.2 a 0.4 | de 0.4 a 0.6 | de 0.6 a 0.8 | de 0.8 a 1
Number of Injecting drug users on opioid substitution therapy that receive at least 3 support services from NGOs working in DUs rehabilitation (Numărul de CDI care sunt în terapia de substituţie cu metadonă şi primesc cel puţin 3 servicii de suport din partea ONG-urilor care lucrează la reabilitarea CDI) |  |  | 711 | 632 | 88.89% |  |  | During S8 a total of 53 PWIDs on opioid substitution therapy (primarily reached) received at least 3 support services from the package (psycho-social support, self-support groups, peer to peer education, distributions of information materials, food support, etc.) offered by NGOs working in PWUDs rehabilitation. The number of PWIDs on OST covered with psycho-social support is directly dependent to the number of PWIDs enrolled in OST treatment (new patients) which is continuously decreasing. During S2, 2013, 50 new clients were enrolled in the substitution therapy program, the number of OST patients covered with support services (primarily reached) being 53 versus 40 planned. The indicator is achieved in proportion of 89%. Reason for variance: The target for the period 8 (40 persons primarily reached) has been exceeded (53 people reached). The underachievement of the cumulative target for the reported period (over program term) is determined by the variation between targets settled and results registered for period one of grant implementation caused by continuously decreasing enrolment of new patients in OST. As the number of OST patients that can be covered with psycho-support services is directly tied to new patients enrolled in OST, the enrolment dynamics in period one has determined and directly impacted the achievement of targets for this indicator and is affecting the results for the reported period as the target is cumulative over program term. (Pe parcursul semestrului 8 un total de 53 CDI aflați în terapia de substituție cu metadonă (primar acoperiți) au primit cel puțin 3 servicii de suport din pachetul serviciilor (suport psiho-social, grupuri de ajutor reciproc, educație de la egal la egal, diseminarea materialelor informaționale, suport alimentar) oferite în cadrul centrelor de zi de către ONG-urile care lucrează în domeniul reabilitării CDI. Numărul de CDI aflați în TSO, acoperiți cu suport psiho-social este direct dependent de numărul CDI înrolați în TSO (cazuri noi), cifra care este în continuă scădere. Pe parcursul S2, 2013, 50 beneficiari noi au fost înrolați în terapia de substituție, numărul de pacienți în TSO acoperiți cu servicii de suport (primari acoperiți) fiind de 53 față de 40 planificați. Indicatorul este atins în proporție de 89%. Cauza variației: Ținta pentru perioada 8 (40 persoane noi primar acoperite) a fost depășită (53 persoane acoperite). Neatingerea țintei cumulative pentru perioada raportată (pe toata perioada grantului) este determinată de variația între țintele stabilite și rezultatele înregistrate pentru perioada întâi de implementare a grantului cauzată de scăderea continua a pacienților înrolați în TSO. Numărul de pacienți în TSO care pot fi acoperiți cu servicii de suport psiho-social este direct proporțional cu numărul pacienților noi înrolați în TSO, dinamica înrolării în perioada întâi a determinat și a afectat direct atingerea țintei pentru acest indicator și afectează rezultatul pentru perioada raportată deoarece ținta propusă se calculează cumulativ pentru toată perioada grantului.) | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of medical (doctors and nurses) and non-medical staff (psychologists, social assistants, peer consultants) trained in HIV/AIDS (Numărul personalului medical (medici şi asistente medicale) şi non-medical (psihologi, asistenţi sociali, educatori de la egal la egal) instruiţi în HIV/SIDA) |  |  | 90 | 86 | 95.56% |  |  | A total of 86 persons were trained in S8, from them: 15 medical staff were trained in international training in Clinica Lavra in Disorders of the CNS, 25 non-medical specialists from south region NRS MDTs, Social regional center and NGO providing care and support to PLHIV were trained in protection and assistance of people living with HIV within the NRS; 15 representatives from NGO that provide HR services to PWIDs, CSWs, LGBT and care to PLHIV were trained in Voluntary counseling and testing; 31 social workers were trained in HIV/TB. The indicator is substantially achieved. Reason for variance: one training for infectious diseases specialists planned under budget line 3.1.4 for S2, 2013, has been conducted in S1, 2013, the organization in advance being conditioned by the fact that the trainings for infectious diseases specialists planned under budget line 3.1.4 were directly related to the reform and reorganization of the HIV medical service provision system, and all three events planned for year 2013 (2 in S1 and 1 in S2) have been organised in S1, 2013. At the same time one additional event has been conducted from savings, with TGF approval (training course on VCT for 15 people). (În total 86 persoane au fost instruite în semestrul 8, dintre care: 15 lucrători medicali au participat la curs de instruire internațional organizat la Clinica Lavra pe Maladiile sistemului nervos central în cadrul infecţiei cu HIV; 25 lucrători non-medicali din echipele multidisciplinare ale SNR din regiunea de sud, din CSR și ONG care oferă servicii de îngrijirea şi suportul PTH au fost instruiţi în protecţia şi asistenţa persoanelor care trăiesc cu HIV în cadrul CSR; 15 reprezentanți ai ONG-urilor care oferă servicii pentru PCDI, LSC, BSM și îngrijire și suport PTH au fost instruiți în consiliere şi testare voluntară, 31 lucrători sociali au fost instruiți în HIV/TB. Indicatorul este substanţial atins. Cauza variației: o instruire pentru medicii infecţionişti planificată în cadrul liniei bugetare 3. 1. 4 pentru S2, 2013, a fost organizată în S1, 2013, organizarea în avans fiind condiţionată de faptul că instruirile pentru infecţionişti planificate în cadrul liniei bugetare 3. 1. 4 au fost direct legate de reforma şi de reorganizarea sistemului de prestare a serviciilor medicale HIV şi toate trei evenimente planificate pentru anul 2013 (două în S1 şi unul în S2) au fost organizate în timpul S1, 2013. În acelaşi timp un eveniment adiţional a fost organizat din economii, cu aprobarea FG (curs de instruire în VCT pentru 15 persoane) | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number of PLHIV receiving food parcels to improve ARV treatment adherence (Numărul de PTH care primesc pachete alimentare pentru a îmbunătăți aderenţa la tratamentul ARV) |  |  | 1040 | 948 | 91.15% |  |  | A total of 948 PLHIV received food parcels during year 2013, out of them 106 primarily reached during S8. Each quarter 800 PLHIV, from both civilian and penitentiary sectors, selected based on socio-economic vulnerability, benefit of food parcels for better adherence to treatment. The indicator is substantially achieved. The reason for variance: The target for this indicator is annual and has been calculated based on an estimated quarterly increase by 10% in the number of new beneficiaries which usually come from the ranks of new ART enrolled patients. 800 food parcels are distributed quarterly to PLHIV, selected based on a set of unique socio-economic vulnerability criteria. Subject to the degree of vulnerability the ranking of potential beneficiaries changes from one quarter to another, including previously reached and primarily reached beneficiaries (mostly from those newly enrolled in ART) that ranks in the top 800 most vulnerable ART patients. (În total 948 PTH au primit pachete alimentare pe parcursul anului 2013, din ei 106 primar acoperiți pe parcursul S8. În fiecare trimestru 800 PTH, din sectorul civil şi penitenciar, selectate în baza vulnerabilității socio-economice, beneficiază de pachete alimentare pentru o aderență mai bună la tratament. Indicatorul este substanţial realizat. Cauza variației: ţinta pentru acest indicator este anuala şi a fost calculată în baza unei creşteri trimestriale estimate de 10% a număruuil de beneficiari noi care, de regulă, sunt slectaţi din răndul pacienţilor noi înrolaţi în ARV. 800 pachete alimentare sunt distribuite trimestrial PTH, selectate pe baza unui set de criterii unice de vulnerabilitate socio-economice. În funcţie de gradul de vulnerabilitate, clasamentul potenţialilor beneficiari se schimbă de la un trimestru la altul, inclusiv pentru beneficiarii acoperiţi antrerior sau primar (mai ales din răndul pacienţiilor noi înrolaţi în ART) care se clasează în topul celor mai vulnerabili 800 pacienţii în ART.) | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Number and percentage of individuals currently on OST who have been on OST continuously at least 6 months for the past 12 months (Numărul şi procentul persoanelor aflate în tratamentul de substituție cu metadonă (TSO) care au fost în TSO continuu cel puțin 6 luni pe parcursul ultimelor 12 luni) |  |  | 60% | 47% | 78.33% |  |  | A total of 47 individuals out of 100 that initiated OST during Semester 1, 2013 have completing at least 6 months of continuous treatment on OST. Currently OST is provided in three sites: Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (in 12 penitentiary institutions: #1 Taraclia, #3 Leova, #4 Cricova, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Balti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Branesti, #13 Chisinau). The indicator is partially achieved (78%). Reason for variance: the rate of retention in treatment is determined by a series of factors, namely: seasonal migration of patients (both abroad and in country), emergency of seasonal illicit drugs on black market, low doses of methadone (below recommended 60mg minimal average dose), and concurrent use of illicit drugs, methadone distribution restricted to OST site or all patients including for drug users in stable remission, repeated enrollment in treatment without prior psycho-social support to prepare the patient for the next attempt, misconceptions about OST in both medical and psych-social support teams, negative image of OST among PWID, etc. (În total 47 persoane din 100 care au inițiat TSO în timpul semestrului 1, 2013 au finalizat cel puțin 6 luni de TSO continuu. Actualmente TSO este distribuită in trei site-uri: Dispensarul Republican de Narcologie, Spitalul Municipal Bălţi şi Departamentul Instituțiilor Penitenciare (în 12 institutii penitenciare: #1 Taraclia, #3 Leova, #4 Cricova, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Balti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Brănești, #13 Chișinău). Indicatorul este atins parțial (78%). Cauza variației: rata de retenție în tratament este determinată de o serie de factori, și anume: migrația sezonieră a pacienților (atât peste hotare cât și în interiorul țarii), apariţia drogurilor ilicite sezoniere pe piața neagră, doze mici de metadonă (mai puțin decât doza minimă recomandată de 60mg), precum și utilizarea concomitentă a drogurilor ilicite, distribuția metadonei limitată la punctul de distribuţie a TSO, inclusiv pentru consumatorii de droguri în remisie stabila, înrolare repetată în tratament fără suport psiho-social preventiv pentru a pregăti pacientul pentru următoarea încercare, concepții greșite despre TSO atât în echipele medicale cat și cele de asistență psiho-socială, imaginea negativă a TSO printre CDI, etc.) | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of human rights strategic litigation cases for PLWH initiated (Numărul de cazuri de încălcare a drepturilor PTH inițiate pentru litigare strategică) |  |  | 10 | 10 | 100% |  |  | 10 litigation cases have been initiated during S8. The cases were related to disclosure of confidential medical information related to HIV status, unethical and unprofessional behavior of medical staff, refusal to offer medical services, adoption of children by HIV positive persons, inhuman/ degrading treatment of detained PLHIV, etc. The indicator is achieved. (Pe parcursul semestrului 8, au fost inițiate 10 litigii. Cazurile au fost legate de divulgarea informației medicale confidențiale legate de statutul HIV, comportament neetic și neprofesional al personalului medical, refuzul de a acorda servicii medicale, problema adopției copiilor de către persoane HIV pozitive, tratament inuman/degradant față de deținuții HIV pozitivi, etc. Indicatorul este atins.) | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of PLHIV assisted by legal aid (consultancies offered by legal network) (Numărul de PTH care au beneficiat de asistență juridică) |  |  | 70 | 114 | 162.9% |  |  | A total of 114 consultancies were offered remotely by traveling to project sites of 4 lawyers, during S8; they offered legal assistance related to issues of legal, civil (including disclosure of HIV status), administrative nature to all PLHIV in need. The indicator is overachieved. Reason for variance: The number of consultancies offered by project lawyers is determined by the request of legal support from PLHIV and can vary from one period to another. With the opening of Social Regional Centers project lawyer provide services within the Centers facilities (with a specific periodicity) bringing this way services closer to the beneficiary and increasing their access to legal support. The increase in number of consultancies provided has no financial impact as the layers are fool day project consultants with fix remuneration. (Pe parcursul semestrului 8 au fost prestate 114 consultații în teren de către 4 avocați. Ei au oferit asistență juridică pe aspecte de natură legală, civilă (inclusiv divulgarea statutului HIV) şi administrative tuturor PTH care au solicitat asistență juridici). Indicatorul este depășit. Cauza variației: Numărul de consultații oferite de către avocații proiectului este determinat de cererea de asistență juridică din partea PTH și poate varia de la o perioadă la alta. Odată cu deschiderea Centrelor Sociale Regionale avocații prestează servicii în cadrul centrelor (cu o anumită periodicitate) aducând astfel serviciile mai aproape de beneficiar și crescând accesul la asistența juridică. Creșterea numărului de servicii de consultanță juridică prestate nu are impact financiar deoarece avocații sunt angajați în proiect cu zi deplină de lucru şi au remunerare fixă.) | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Number of members of the civil society trained in services provision to PLHIV (Numărul de membri ai societăţii civile instruiţi în furnizarea de servicii pentru PTH) |  |  | 50 | 54 | 108% |  |  | A total number of 54 representatives of organizations that provide services to PLHIV and key populations were trained in S8, from them: 27 people were trained in Communication and Advocacy and 27 people were trained in Case management. The indicator is overachieved. Reason for variance: due the interest from community organizations and the fact that the costs for the selected venue allowed to increase the number of participants, a higher number of people (27) have been included in each events compared to 25 planned. (În total 54 reprezentanți ai organizațiilor care prestează servicii PTH şi ai populațiilor cheie au fost instruiți pe parcursul S8. 27 reprezentanți ai societății civile au fost instruiți în Comunicare și Advocacy și 27 membri în Managementul Cazului cu HIV. Indicatorul este depășit. Cauza variației: numărul persoanelor interesate în tematica instruirii a fost mai mare decât cel planificat şi datorită faptului că costurile de desfășurare ale evenimentului au permis încadrarea mai multor participanţi, numărul participanților pentru fiecare instruire a fost mai mare (27) faţă de 25 planificaţi.) | [5 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
[14 empty] | #N/A | #N/A | #N/A | #N/A | #N/A
Menu

## Recommendations
Dashboard: Moldova - HIV / AIDS
SSF (Round 8) | Period 2 |  |  |  |  | Report Period: | P8
Latest Rating: | A2 |  | PAS Center |  |  | From: | July 01, 2013
|  |  | Reducing HIV-related burden in the Republic of Moldova |  |  | To: | December 31, 2013
Recommendations
Are all funds reaching implementation levels and being spent according to budget?
Financial |  | Summary Comments |  |  | Recommendations
F1 |  | By December 31, 2013, the total amount disbursed by TGF to PAS Center was EUR 10,565,583. The cumulative disbursement rate is 104.6%. The variance is due to the fact that the cumulative disbursement includes the buffer for Q1, 2014 in a total amount of EUR 465,363. (Până la 31 decembrie 2013, Centrului PAS i-au fost disbursate de către Fondul Global 10,565,583 Euro. Rata cumulativă a disbursării este de 104.6%. Variația este cauzată de faptul că disbursarea cumulativă include un buffer pentru Tr.1, 2014 în valoare totală de 465,363 Euro.)
F2 |  | The cumulative cash outflow rate as of December 31, 2013 per Objectives range between 98% and 104% the variances being due to payments afferent to commitments from Period 1, advanced payments from year 2014 budget and commitments that will be paid over next semester. (Rata cumulativă de absorbţie din buget la 31.12.2013 per Obiective este între 98% şi 104% variaţia datorînduse în mare parte plăţilor aferente Perioadei 1, plăților în avans din bugetul anului 2014 și angajamentelor care vor fi plătite pe parcursul semestrului următor.)
F3 |  | The cash outflow rate for the reporting period is 98.3% (actual: EUR 992,657, budget: EUR 1,009,491) of the semi-annual budget and the cumulative cash outflow as of December 31, 2013 is 100.56% (actual: EUR 10,159,549, budget: EUR 10,102,673). The cumulative variance mainly consist of payments afferent to commitments from Period 1, payments the NGO "Youth for the Wright to Live" from year 2014 budget as per TGF approval dated February 20, 2013 for the renovation, and commitments that will be paid over next semester. (Rata de absorbţie pentru perioada raportată este de 98.3% (Actual 992,657 Euro/Budget 1,009,491 Euro) din bugetul semianual şi rata cumulativă de absorbţie din buget la 31.12.2013 este 100.56% (actual: 10,159,549 Euro, budget: 10,102,673 Euro). Variația cumulativă se datorează în mare parte plăţilor aferente Perioadei 1, plăților din bugetul anului 2014 către ONG-ul "Tinerii pentru Dreptul la Viață" pentru renovare conform aprobării FG din data de 20 februarie 2013 și angajamentelor care vor fi plătite pe parcursul semestrului următor.)
F4 |  | The PU for Semester 2, 2013 has been submitted to LFA in due terms (42 days after the end of reported period), on February 11, 2014. The disbursement requested with the previous PU/DR for S2, 2012 (submitted on February 15, 2013) reached the PR on 08 May, 2013 (83 days after the PU/DR) and include the budget for semester 2, 2013 and the buffer for Q1, 2014. (Actualizarea progresului pentru Semestrul 2, 2013 a fost remisa Agentului Local al Fondului in termenii stabiliți (42 de zile după finisarea perioadei raportate) pe data de 11 februarie 2013. Disbursarea solicitată cu precedenta Actualizare de progres (PU/DR) pentru Semestrul 2, 2012 a fost primită de PR pe data de 08 mai 2013 (83 zile de la PU/DR). Disbursarea include bugetul pentru semestrul 2, 2013 și un buffer pentru Tr.1, 2014.)
Are procurement and hiring on schedule?
Management |  | Summary Comments |  |  | Recommendations
M1 |  | The two special conditions afferent to Period 2 have been fulfilled in strict accordance with their provisions. (Cele două condiții speciale aferente Perioadei 2 au fost îndeplinite, în strictă conformitate cu prevederile contractuale.)
M2 |  | Two full time positions and 12 part time. (Două poziţii cu normă plină şi 12 - parţială.) | #DIV/0! | #DIV/0!
M3 |  | Four Sub-recipients (SRs) have been identified initialy (2010) to implement different components within the program: Soros Foundation-Moldova (SFM); League of people living with HIV of Moldova; New Life, Moldovan Institute for Human Rights. One SR (SFM) has been earlier assessed by the governmental PR of GF grants as it acts as an SR since GF Round one. Two other SRs have been assessed (New Life and Moldovan Institute for Human Rights) by PAS Center the last one (League of people living with HIV of Moldova) by TGF Local Fund Agent. Four sub-grant agreements have been signe following the assessment. In September 2011, due to lack of capacity for adequate implementation of the grant portion contracted the sub-grant agreement with one of the SRs (League of people living with HIV) was terminated and the management of activities has been entrusted to an other SR ( SFM). Respectively three sub-recipients continued to receive funds till the end of Period one (December 31, 2012). During renewal one SR component has been reorganised and starting with Period two (2013) there are two SRs that receiv funds within the grant. (Patru Sub-Recipienţi (SR), au fost identificaţi inițial (2010) pentru a implementa diferite componente în cadrul programului: Fundația Soros-Moldova (FSM), Liga persoanelor care trăiesc cu HIV din Moldova, Viaţa Nouă, Institutul pentru Drepturile Omului din Moldova. Un SR (SFM) a fost evaluat anterior de către RP guvernamental, deoarece activează în calitate de SR începănd cu Runda 1. Alţi doi SR au fost evaluaţi (Viaţa Nouă și Institutul pentru Drepturile Omului din Moldova) de către Centrul PAS iar ultimul (Liga persoanelor care trăiesc cu HIV din Republica Moldova) de către Agentul Local al Fondului Global. Urmare a evaluării au fost semnate patru acorduri de sub-grant. În septembrie 2011, din cauza lipsei capacității de implementare adecvată a componentului de grant contractat, acordul de sub-finantare cu unul dintre SR (Liga persoanelor care trăiesc cu HIV) a fost reziliat și gestionarea activităților a fost încredințată altui SR (SFM). Respectiv trei SR au primit fonduri până la finele Perioadei unu (31 decembrie 2012). La etapa de reînoire a grantului, componentul implementat de unul dintre acesti SR a fost reorganizat și începănd cu Perioada 2 (2013) doi SR primesc resurse din cadrul grantului trei SR.
M4 |  | The SRs’ quarterly reports (financial report, activity report and performance framework) are due to the PR not later than 25 days after the close of each quarter and are generally submitted in time. The clearance period vary from one SR to an other subject to the completeness and consistence of the reports. For the SR SFM the Sub-subrecipients financial reports are due quarterly and can be submitted during the following quarter, the activity reports are due not later than 10 days from the end of each month and are generally submitted in time except one Ssr - NGO Master in Public Health – that is constantly late in reporting. During the reporting period reflected in this dashboard 16 reports from 17 due were submited in time. For the SR New Life the reports (financial, activity and indicators) are due not later than 15 days after the close of each quarter and are generally submitted in time. (Rapoartele trimestriale ale SR-ului (raport financiar, raport de activitate și cadrul de performanță) urmează a fi transmise RP nu mai târziu de 25 de zile de la încheierea fiecărui trimestru. Rapoartele sunt de regulă prezentate la timp. Perioada de verificare şi aprobare variază de la un SR la altul în funcţie de exhaustivitatea și consistența rapoartelor. Pentru SR-ul FSM rapoartele financiare ale Sub-subrecipienţilor (Ssr) urmează a fi transmise trimestrial și pot fi prezentate în trimestrul următor, rapoartele de activitate urmează a fi prezentate nu mai târziu de 10 zile de la sfârșitul fiecărei luni și sunt în general prezentate la timp cu excepția unui Ssr - ONG-ul Master în Sănătatea Publică - care întârzie raportarea în mod constant . Pe parcursul perioadei de raportare reflectată în aces raport, 16 raporte din 17 planificate au fost transmise la timp. Pentru SR-ul Viaţa Nouă rapoartele (financiar, de activitate și indicatorii) urmează a fi prezentate nu mai târziu de 15 zile de la încheierea fiecărui trimestru și sunt, de regulă, prezentate la timp.)
M5 |  | N/A
M6 |  | N/A
Are technical targets being achieved?
Programmatic |  | Summary Comments |  |  | Recommendations
P1 - trend |  | During S8 a total 359 PLHIV were primarily reached with care and support services through four social regional centers providing assistance to PLHIV and 10 territorial organizations that ensures outreach to PLHIV and their families. The beneficiaries are provided with the following services: psycho-social counseling and support, medical counseling and referral, distribution of information materials, peer counseling, self-support groups and food support, etc. The indicator is achieved. (Pe parcursul semestrului 8, un total de 359 PTH au fost primar acoperiți cu servicii de îngrijire şi suport prestate în cadrul celor patru Centre Sociale Regionale şi a 10 organizații teritoriale care prestează servicii direct PTH și membrilor familiilor lor. Beneficiarilor le sunt prestate următoarele servicii: suport și consiliere psiho-socială, consiliere medicală și referiri, diseminarea materialelor informaționale şi consiliere de la egal la egal, grupuri de ajutor reciproc și suport alimentar, etc. Indicatorul este atins.)
P2 - trend |  | A total of 325 children (109 infected and 216 affected by HIV) received social support during year 2013 (primarily reached), out of them 61 (13 infected and 48 affected by HIV) primarily reached during S8. Each quarter 230 children (all HIV infected children that can be reached and the majority of children born from HIV infected mother with unknown status) benefit of food parcels. At the same time each semester HIV positive children benefit of a set of stationary and clothing for school as part of social support program. During reported period the number of HIV positive children that benefited of clothing and school supplies was 109, exceeding by 14 the planned number of 95. This fact has determined the need to reallocate additional budget (from savings under other budget lines targeted at PLHIV support) in order to cover fourteen additional sets of clothing and school supplies. The indicator is overachieved. Reason for variance: The number of children primarily reached with social support is determined by the number of children diagnosed with HIV that are reached and by the number of children born from HIV positive mothers immediately before and during the reported period. During reported period the number of HIV positive children reached was 109, exceeding by fourteen the planned number of 95. Note: In Peroada 1 the targets were cumulative over program term, but starting with Period 2 - the targets are cumulative annually. (Un total de 325 copii (109 copii HIV infectați și 216 copii afectați de HIV) au beneficiat de suport social pe parcursul anului 2013 (acoperiți primar), dintre care 61 (13 infectati și 48 afectati de HIV) primari acoperiti in S8. În același timp, în fiecare trimestru, 230 copii (toți copiii infectați cu HIV, care pot fi acoperiți cu servicii, și majoritatea copiilor născuți din mame HIV pozitive) beneficiază semestrial de un set de haine şi rechizite școlare ca parte a programului de acordare a suportului social. Pe parcursul perioadei de raportare, numărul de copii HIV infectați care au primit cîte un set de haine şi rechizite școlare a crescut la 109, depășind cu 14 unități numărul planificat de 95. Acest fapt a determinat necesitatea realocării unui buget adițional (din economiile obținute în cadrul altor linii bugetare orientate către suportul PTH) pentru a acoperi patrusprezece seturi suplimentare de îmbrăcăminte şi rechizite școlare. Indicatorul este depășit. Cauza variației: Numărul de copii primar acoperiți cu suport social este determinat de numărul de copii diagnosticați cu HIV și numărul copiilor născuți din mame HIV pozitive imediat înainte și în perioada de raportate. Pe parcursul perioadei de raportare numarul copiilor HIV pozitivi acoperiți cu servicii a fost 109, depasit cu 14 numarul planificat de 95.) Notă: În Peroada 1, tintele erau cumulative pe durata programului, iar începînd cu Perioada 2 - tintele sunt cumulative anual.
P3 - trend |  | During S8 a total of 53 PWIDs on opioid substitution therapy (primarily reached) received at least 3 support services from the package (psycho-social support, self-support groups, peer to peer education, distributions of information materials, food support, etc.) offered by NGOs working in PWUDs rehabilitation. The number of PWIDs on OST covered with psycho-social support is directly dependent to the number of PWIDs enrolled in OST treatment (new patients) which is continuously decreasing. During S2, 2013, 50 new clients were enrolled in the substitution therapy program, the number of OST patients covered with support services (primarily reached) being 53 versus 40 planned. The indicator is achieved in proportion of 89%. Reason for variance: The target for the period 8 (40 persons primarily reached) has been exceeded (53 people reached). The underachievement of the cumulative target for the reported period (over program term) is determined by the variation between targets settled and results registered for period one of grant implementation caused by continuously decreasing enrolment of new patients in OST. As the number of OST patients that can be covered with psycho-support services is directly tied to new patients enrolled in OST, the enrolment dynamics in period one has determined and directly impacted the achievement of targets for this indicator and is affecting the results for the reported period as the target is cumulative over program term. (Pe parcursul semestrului 8 un total de 53 CDI aflați în terapia de substituție cu metadonă (primar acoperiți) au primit cel puțin 3 servicii de suport din pachetul serviciilor (suport psiho-social, grupuri de ajutor reciproc, educație de la egal la egal, diseminarea materialelor informaționale, suport alimentar) oferite în cadrul centrelor de zi de către ONG-urile care lucrează în domeniul reabilitării CDI. Numărul de CDI aflați în TSO, acoperiți cu suport psiho-social este direct dependent de numărul CDI înrolați în TSO (cazuri noi), cifra care este în continuă scădere. Pe parcursul S2, 2013, 50 beneficiari noi au fost înrolați în terapia de substituție, numărul de pacienți în TSO acoperiți cu servicii de suport (primari acoperiți) fiind de 53 față de 40 planificați. Indicatorul este atins în proporție de 89%. Cauza variației: Ținta pentru perioada 8 (40 persoane noi primar acoperite) a fost depășită (53 persoane acoperite). Neatingerea țintei cumulative pentru perioada raportată (pe toata perioada grantului) este determinată de variația între țintele stabilite și rezultatele înregistrate pentru perioada întâi de implementare a grantului cauzată de scăderea continua a pacienților înrolați în TSO. Numărul de pacienți în TSO care pot fi acoperiți cu servicii de suport psiho-social este direct proporțional cu numărul pacienților noi înrolați în TSO, dinamica înrolării în perioada întâi a determinat și a afectat direct atingerea țintei pentru acest indicator și afectează rezultatul pentru perioada raportată deoarece ținta propusă se calculează cumulativ pentru toată perioada grantului.)
P1 |  | During S8 a total 359 PLHIV were primarily reached with care and support services through four social regional centers providing assistance to PLHIV and 10 territorial organizations that ensures outreach to PLHIV and their families. The beneficiaries are provided with the following services: psycho-social counseling and support, medical counseling and referral, distribution of information materials, peer counseling, self-support groups and food support, etc. The indicator is achieved. (Pe parcursul semestrului 8, un total de 359 PTH au fost primar acoperiți cu servicii de îngrijire şi suport prestate în cadrul celor patru Centre Sociale Regionale şi a 10 organizații teritoriale care prestează servicii direct PTH și membrilor familiilor lor. Beneficiarilor le sunt prestate următoarele servicii: suport și consiliere psiho-socială, consiliere medicală și referiri, diseminarea materialelor informaționale şi consiliere de la egal la egal, grupuri de ajutor reciproc și suport alimentar, etc. Indicatorul este atins.)
P2 |  | A total of 325 children (109 infected and 216 affected by HIV) received social support during year 2013 (primarily reached), out of them 61 (13 infected and 48 affected by HIV) primarily reached during S8. Each quarter 230 children (all HIV infected children that can be reached and the majority of children born from HIV infected mother with unknown status) benefit of food parcels. At the same time each semester HIV positive children benefit of a set of stationary and clothing for school as part of social support program. During reported period the number of HIV positive children that benefited of clothing and school supplies was 109, exceeding by 14 the planned number of 95. This fact has determined the need to reallocate additional budget (from savings under other budget lines targeted at PLHIV support) in order to cover fourteen additional sets of clothing and school supplies. The indicator is overachieved. Reason for variance: The number of children primarily reached with social support is determined by the number of children diagnosed with HIV that are reached and by the number of children born from HIV positive mothers immediately before and during the reported period. During reported period the number of HIV positive children reached was 109, exceeding by fourteen the planned number of 95. Note: In Peroada 1 the targets were cumulative over program term, but starting with Period 2 - the targets are cumulative annually. (Un total de 325 copii (109 copii HIV infectați și 216 copii afectați de HIV) au beneficiat de suport social pe parcursul anului 2013 (acoperiți primar), dintre care 61 (13 infectati și 48 afectati de HIV) primari acoperiti in S8. În același timp, în fiecare trimestru, 230 copii (toți copiii infectați cu HIV, care pot fi acoperiți cu servicii, și majoritatea copiilor născuți din mame HIV pozitive) beneficiază semestrial de un set de haine şi rechizite școlare ca parte a programului de acordare a suportului social. Pe parcursul perioadei de raportare, numărul de copii HIV infectați care au primit cîte un set de haine şi rechizite școlare a crescut la 109, depășind cu 14 unități numărul planificat de 95. Acest fapt a determinat necesitatea realocării unui buget adițional (din economiile obținute în cadrul altor linii bugetare orientate către suportul PTH) pentru a acoperi patrusprezece seturi suplimentare de îmbrăcăminte şi rechizite școlare. Indicatorul este depășit. Cauza variației: Numărul de copii primar acoperiți cu suport social este determinat de numărul de copii diagnosticați cu HIV și numărul copiilor născuți din mame HIV pozitive imediat înainte și în perioada de raportate. Pe parcursul perioadei de raportare numarul copiilor HIV pozitivi acoperiți cu servicii a fost 109, depasit cu 14 numarul planificat de 95.) Notă: În Peroada 1, tintele erau cumulative pe durata programului, iar începînd cu Perioada 2 - tintele sunt cumulative anual.
P3 |  | During S8 a total of 53 PWIDs on opioid substitution therapy (primarily reached) received at least 3 support services from the package (psycho-social support, self-support groups, peer to peer education, distributions of information materials, food support, etc.) offered by NGOs working in PWUDs rehabilitation. The number of PWIDs on OST covered with psycho-social support is directly dependent to the number of PWIDs enrolled in OST treatment (new patients) which is continuously decreasing. During S2, 2013, 50 new clients were enrolled in the substitution therapy program, the number of OST patients covered with support services (primarily reached) being 53 versus 40 planned. The indicator is achieved in proportion of 89%. Reason for variance: The target for the period 8 (40 persons primarily reached) has been exceeded (53 people reached). The underachievement of the cumulative target for the reported period (over program term) is determined by the variation between targets settled and results registered for period one of grant implementation caused by continuously decreasing enrolment of new patients in OST. As the number of OST patients that can be covered with psycho-support services is directly tied to new patients enrolled in OST, the enrolment dynamics in period one has determined and directly impacted the achievement of targets for this indicator and is affecting the results for the reported period as the target is cumulative over program term. (Pe parcursul semestrului 8 un total de 53 CDI aflați în terapia de substituție cu metadonă (primar acoperiți) au primit cel puțin 3 servicii de suport din pachetul serviciilor (suport psiho-social, grupuri de ajutor reciproc, educație de la egal la egal, diseminarea materialelor informaționale, suport alimentar) oferite în cadrul centrelor de zi de către ONG-urile care lucrează în domeniul reabilitării CDI. Numărul de CDI aflați în TSO, acoperiți cu suport psiho-social este direct dependent de numărul CDI înrolați în TSO (cazuri noi), cifra care este în continuă scădere. Pe parcursul S2, 2013, 50 beneficiari noi au fost înrolați în terapia de substituție, numărul de pacienți în TSO acoperiți cu servicii de suport (primari acoperiți) fiind de 53 față de 40 planificați. Indicatorul este atins în proporție de 89%. Cauza variației: Ținta pentru perioada 8 (40 persoane noi primar acoperite) a fost depășită (53 persoane acoperite). Neatingerea țintei cumulative pentru perioada raportată (pe toata perioada grantului) este determinată de variația între țintele stabilite și rezultatele înregistrate pentru perioada întâi de implementare a grantului cauzată de scăderea continua a pacienților înrolați în TSO. Numărul de pacienți în TSO care pot fi acoperiți cu servicii de suport psiho-social este direct proporțional cu numărul pacienților noi înrolați în TSO, dinamica înrolării în perioada întâi a determinat și a afectat direct atingerea țintei pentru acest indicator și afectează rezultatul pentru perioada raportată deoarece ținta propusă se calculează cumulativ pentru toată perioada grantului.)
P4 |  | A total of 86 persons were trained in S8, from them: 15 medical staff were trained in international training in Clinica Lavra in Disorders of the CNS, 25 non-medical specialists from south region NRS MDTs, Social regional center and NGO providing care and support to PLHIV were trained in protection and assistance of people living with HIV within the NRS; 15 representatives from NGO that provide HR services to PWIDs, CSWs, LGBT and care to PLHIV were trained in Voluntary counseling and testing; 31 social workers were trained in HIV/TB. The indicator is substantially achieved. Reason for variance: one training for infectious diseases specialists planned under budget line 3.1.4 for S2, 2013, has been conducted in S1, 2013, the organization in advance being conditioned by the fact that the trainings for infectious diseases specialists planned under budget line 3.1.4 were directly related to the reform and reorganization of the HIV medical service provision system, and all three events planned for year 2013 (2 in S1 and 1 in S2) have been organised in S1, 2013. At the same time one additional event has been conducted from savings, with TGF approval (training course on VCT for 15 people). (În total 86 persoane au fost instruite în semestrul 8, dintre care: 15 lucrători medicali au participat la curs de instruire internațional organizat la Clinica Lavra pe Maladiile sistemului nervos central în cadrul infecţiei cu HIV; 25 lucrători non-medicali din echipele multidisciplinare ale SNR din regiunea de sud, din CSR și ONG care oferă servicii de îngrijirea şi suportul PTH au fost instruiţi în protecţia şi asistenţa persoanelor care trăiesc cu HIV în cadrul CSR; 15 reprezentanți ai ONG-urilor care oferă servicii pentru PCDI, LSC, BSM și îngrijire și suport PTH au fost instruiți în consiliere şi testare voluntară, 31 lucrători sociali au fost instruiți în HIV/TB. Indicatorul este substanţial atins. Cauza variației: o instruire pentru medicii infecţionişti planificată în cadrul liniei bugetare 3. 1. 4 pentru S2, 2013, a fost organizată în S1, 2013, organizarea în avans fiind condiţionată de faptul că instruirile pentru infecţionişti planificate în cadrul liniei bugetare 3. 1. 4 au fost direct legate de reforma şi de reorganizarea sistemului de prestare a serviciilor medicale HIV şi toate trei evenimente planificate pentru anul 2013 (două în S1 şi unul în S2) au fost organizate în timpul S1, 2013. În acelaşi timp un eveniment adiţional a fost organizat din economii, cu aprobarea FG (curs de instruire în VCT pentru 15 persoane)
P5 |  | A total of 948 PLHIV received food parcels during year 2013, out of them 106 primarily reached during S8. Each quarter 800 PLHIV, from both civilian and penitentiary sectors, selected based on socio-economic vulnerability, benefit of food parcels for better adherence to treatment. The indicator is substantially achieved. The reason for variance: The target for this indicator is annual and has been calculated based on an estimated quarterly increase by 10% in the number of new beneficiaries which usually come from the ranks of new ART enrolled patients. 800 food parcels are distributed quarterly to PLHIV, selected based on a set of unique socio-economic vulnerability criteria. Subject to the degree of vulnerability the ranking of potential beneficiaries changes from one quarter to another, including previously reached and primarily reached beneficiaries (mostly from those newly enrolled in ART) that ranks in the top 800 most vulnerable ART patients. (În total 948 PTH au primit pachete alimentare pe parcursul anului 2013, din ei 106 primar acoperiți pe parcursul S8. În fiecare trimestru 800 PTH, din sectorul civil şi penitenciar, selectate în baza vulnerabilității socio-economice, beneficiază de pachete alimentare pentru o aderență mai bună la tratament. Indicatorul este substanţial realizat. Cauza variației: ţinta pentru acest indicator este anuala şi a fost calculată în baza unei creşteri trimestriale estimate de 10% a număruuil de beneficiari noi care, de regulă, sunt slectaţi din răndul pacienţilor noi înrolaţi în ARV. 800 pachete alimentare sunt distribuite trimestrial PTH, selectate pe baza unui set de criterii unice de vulnerabilitate socio-economice. În funcţie de gradul de vulnerabilitate, clasamentul potenţialilor beneficiari se schimbă de la un trimestru la altul, inclusiv pentru beneficiarii acoperiţi antrerior sau primar (mai ales din răndul pacienţiilor noi înrolaţi în ART) care se clasează în topul celor mai vulnerabili 800 pacienţii în ART.)
P6 |  | A total of 47 individuals out of 100 that initiated OST during Semester 1, 2013 have completing at least 6 months of continuous treatment on OST. Currently OST is provided in three sites: Republican Narcological Dispensary, Balti Municipal Hospital and the Department of Penitentiary Institutions (in 12 penitentiary institutions: #1 Taraclia, #3 Leova, #4 Cricova, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Balti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Branesti, #13 Chisinau). The indicator is partially achieved (78%). Reason for variance: the rate of retention in treatment is determined by a series of factors, namely: seasonal migration of patients (both abroad and in country), emergency of seasonal illicit drugs on black market, low doses of methadone (below recommended 60mg minimal average dose), and concurrent use of illicit drugs, methadone distribution restricted to OST site or all patients including for drug users in stable remission, repeated enrollment in treatment without prior psycho-social support to prepare the patient for the next attempt, misconceptions about OST in both medical and psych-social support teams, negative image of OST among PWID, etc. (În total 47 persoane din 100 care au inițiat TSO în timpul semestrului 1, 2013 au finalizat cel puțin 6 luni de TSO continuu. Actualmente TSO este distribuită in trei site-uri: Dispensarul Republican de Narcologie, Spitalul Municipal Bălţi şi Departamentul Instituțiilor Penitenciare (în 12 institutii penitenciare: #1 Taraclia, #3 Leova, #4 Cricova, #6 Soroca, #7 Rusca, #9 Pruncul, #11 Balti, #15 Cricova, #16 Pruncul, #17 Rezina, #18 Brănești, #13 Chișinău). Indicatorul este atins parțial (78%). Cauza variației: rata de retenție în tratament este determinată de o serie de factori, și anume: migrația sezonieră a pacienților (atât peste hotare cât și în interiorul țarii), apariţia drogurilor ilicite sezoniere pe piața neagră, doze mici de metadonă (mai puțin decât doza minimă recomandată de 60mg), precum și utilizarea concomitentă a drogurilor ilicite, distribuția metadonei limitată la punctul de distribuţie a TSO, inclusiv pentru consumatorii de droguri în remisie stabila, înrolare repetată în tratament fără suport psiho-social preventiv pentru a pregăti pacientul pentru următoarea încercare, concepții greșite despre TSO atât în echipele medicale cat și cele de asistență psiho-socială, imaginea negativă a TSO printre CDI, etc.)
P7 |  | 10 litigation cases have been initiated during S8. The cases were related to disclosure of confidential medical information related to HIV status, unethical and unprofessional behavior of medical staff, refusal to offer medical services, adoption of children by HIV positive persons, inhuman/ degrading treatment of detained PLHIV, etc. The indicator is achieved. (Pe parcursul semestrului 8, au fost inițiate 10 litigii. Cazurile au fost legate de divulgarea informației medicale confidențiale legate de statutul HIV, comportament neetic și neprofesional al personalului medical, refuzul de a acorda servicii medicale, problema adopției copiilor de către persoane HIV pozitive, tratament inuman/degradant față de deținuții HIV pozitivi, etc. Indicatorul este atins.)
P8 |  | A total of 114 consultancies were offered remotely by traveling to project sites of 4 lawyers, during S8; they offered legal assistance related to issues of legal, civil (including disclosure of HIV status), administrative nature to all PLHIV in need. The indicator is overachieved. Reason for variance: The number of consultancies offered by project lawyers is determined by the request of legal support from PLHIV and can vary from one period to another. With the opening of Social Regional Centers project lawyer provide services within the Centers facilities (with a specific periodicity) bringing this way services closer to the beneficiary and increasing their access to legal support. The increase in number of consultancies provided has no financial impact as the layers are fool day project consultants with fix remuneration. (Pe parcursul semestrului 8 au fost prestate 114 consultații în teren de către 4 avocați. Ei au oferit asistență juridică pe aspecte de natură legală, civilă (inclusiv divulgarea statutului HIV) şi administrative tuturor PTH care au solicitat asistență juridici). Indicatorul este depășit. Cauza variației: Numărul de consultații oferite de către avocații proiectului este determinat de cererea de asistență juridică din partea PTH și poate varia de la o perioadă la alta. Odată cu deschiderea Centrelor Sociale Regionale avocații prestează servicii în cadrul centrelor (cu o anumită periodicitate) aducând astfel serviciile mai aproape de beneficiar și crescând accesul la asistența juridică. Creșterea numărului de servicii de consultanță juridică prestate nu are impact financiar deoarece avocații sunt angajați în proiect cu zi deplină de lucru şi au remunerare fixă.)
P9 |  | A total number of 54 representatives of organizations that provide services to PLHIV and key populations were trained in S8, from them: 27 people were trained in Communication and Advocacy and 27 people were trained in Case management. The indicator is overachieved. Reason for variance: due the interest from community organizations and the fact that the costs for the selected venue allowed to increase the number of participants, a higher number of people (27) have been included in each events compared to 25 planned. (În total 54 reprezentanți ai organizațiilor care prestează servicii PTH şi ai populațiilor cheie au fost instruiți pe parcursul S8. 27 reprezentanți ai societății civile au fost instruiți în Comunicare și Advocacy și 27 membri în Managementul Cazului cu HIV. Indicatorul este depășit. Cauza variației: numărul persoanelor interesate în tematica instruirii a fost mai mare decât cel planificat şi datorită faptului că costurile de desfășurare ale evenimentului au permis încadrarea mai multor participanţi, numărul participanților pentru fiecare instruire a fost mai mare (27) faţă de 25 planificaţi.)
P10 |  | #REF!
Menu

## Actions
Dashboard: Moldova - HIV / AIDS
| SSF (Round 8) | Period 2 |  |  |  | Report Period: |  | P8
| Latest Rating: | A2 |  | PAS Center |  | From: |  | July 01, 2013
|  |  | Reducing HIV-related burden in the Republic of Moldova |  |  |  | To: | December 31, 2013
Decisions and Actions
What is the overall status of this grant implementation?
| Key Recommendations from Oversight Group(s) |  |  |  | CCM Decision | Due Date | Person Responsible
Current Reporting Period
Actions to Implement / Previous Period
What is the overall status of this grant implementation?
| CCM Decision |  |  |  | Action Taken | Date | Person Responsible
Previous Reporting Period
Menu

## Setup (hidden)
Dashboard: Moldova - HIV / AIDS
Set-up = List of validation for Grant Detail page
Component | Currency | Round | Phase | Period | Rating | LFA | Medicaments | Countries
Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select | Please Select
HIV / AIDS | $ | Round 1 | Phase 1 | P1 | A1 | CA (Crown Agents) | Isoniazid | Afghanistan
MALARIA | € | Round 2 | Phase 2 | P2 | A2 | DEL (Deloitte) | Ethambutol | Albania
TB |  | Round 3 | RCC | P3 | B1 | DTT (DTT Emerging Markets) | Rifampicin | Algeria
HIVAIDS / TB |  | Round 4 |  | P4 | B2 | FIN (Finconsult) | Pyrazimamide | Angola
HSS |  | Round 5 |  | P5 | C | GT (Grant Thornton) | RDT | Argentina
|  | Round 6 |  | P6 |  | H-C (Hodar-Conseil) | NVP | Armenia
|  | Round 7 |  | P7 |  | KPMG (KPMG) | 3TC | Azerbaijan
|  | Round 8 |  | P8 |  | MSCI (MSCI) | D4T | Bangladesh
|  | Round 9 |  | P9 |  | PwC (PricewaterhouseCoopers) | AZT | Belarus
|  | Round 10 |  | P10 |  | STI (Swiss Tropical Institute), | DDI | Belize
|  |  |  | P11 |  | UNOPS | EFV | Benin
|  |  |  | P12 |  |  | AS/LF | Bhutan
[7 empty] | AS/AQ | Bolivia
[7 empty] | AS/MQ | Bosnia and Herzegovina
[7 empty] | Al/Lum | Botswana
Brazil
[7 empty] | TB nutri'l supplements | Bulgaria
[7 empty] | E-PAP | Burkina Faso
Burundi
Cambodia
Cameroon
Cape Verde
Central African Republic
Chad
Chile
China
China
Colombia
Comoros
Congo (Democratic Republic of the)
Congo (Republic of the)
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Djibouti
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Ethiopia
Fiji
Gabon
Gambia
Georgia
Ghana
Global(LWF)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
India
Indonesia
Iran (Islamic Republic of)
Iraq
Jamaica
Jordan
Kazakhstan
Kenya
Korea, Democratic Peoples Republic of
Kosovo (Serbia)
Kyrgyzstan
Lao PDR
Lesotho
Liberia
Macedonia, FYR
Madagascar
Malawi
Maldives
Mali
Mauritania
Mauritius
Moldova
Mongolia
Montenegro
Morocco
Mozambique
Multi-country Africa (West Africa Corridor Program)
Multi-country Africa(RMCC)
Multi-country Americas (Andean)
Multi-country Americas (CARICOM)
Multi-country Americas (CRN+)
Multi-country Americas (Meso)
Multi-country Americas (OECS)
Multi-country Americas (REDCA+)
Multi-country Western Pacific
Myanmar
Namibia
Nepal
Nicaragua
Niger
Nigeria
Pakistan
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Romania
Russian Federation
Rwanda
Sao Tome and Principe
Senegal
Serbia
Sierra Leone
Solomon Islands
Somalia
South Africa
Sri Lanka
Sudan
Suriname
Swaziland
Syrian Arab Republic
Tajikistan
Tanzania
Thailand
Timor-Leste
Togo
Tunisia
Turkey
Uganda
Ukraine
UN Theme Group on HIV/AIDS (West Bank and Gaza)
Uzbekistan
Viet Nam
Yemen
Zambia
Zanzibar (Tanzania)
Zimbabwe